**Where we are now**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of Department** | **Result sharing workshop to be held on/by** | **Draft SAR completion by** | **External peer review (EPR) by** | **Proposed EPR team** | **Comments**  **(preparation, documentation, assistance needed)** |
| 1 | Department of Accounting & Finance | Thursday, June 8, 2017 | June 2017 | By July 2017 | 1. Foreign EPR: Dr. Chitra Ranjanie  2. Local EPR: Prof. Dr. Devi Narayan Rudra Paul  *3. Subject Expert: Prof. Jahangir Alam, Finance, Chittagong University* |  |
| 2 | Department of Management | Thursday, May 25, 2017  (Demo presentation, final presentation date not announced yet) | June 2017 | By July 2017 | Subject expert name by June 4, 2017 |  |
| 3 | Department of Electrical and Computer Engineering | N/A | June 2017 | By July 2017 | Subject expert name by June 4, 2017 |  |
| 4 | Department of Bio Chemistry and  Microbiology | Wednesday, April 19, 2017 | June 2017 | By July 2017 | Subject expert name by June 4, 2017 |  |
| 5 | Department of Political Science and Sociology | 3rd week of June 2017 | June 2017 | By July 2017 | Subject expert name by June 4, 2017 |  |
| 6 | Department of Pharmaceutical Sciences | Thursday, June 15, 2017 | June 2017 | By July 2017 | Subject expert name by June 4, 2017 |  |
| **Sl. No.** | **Name of Department** | **Result sharing workshop to be held on/by** | **Draft SAR completion by** | **External peer review (EPR) by** | **Proposed EPR team** | **Comments**  **(preparation, documentation, assistance needed)** |
| 7 | Department of Economics | September 2017 | September 2017 | October 2017 | Subject expert name by June 30, 2017 |  |
| 8 | Department of Environmental Science & Management | September 2017 | September 2017 | October 2017 | Subject expert name by June 30, 2017 |  |
| 9 | Department of English & Modern Languages | September 2017 | September 2017 | October 2017 | Subject expert name by June 30, 2017 |  |
| 10 | Department of Marketing & Int’l Business | September 2017 | September 2017 | October 2017 | 1. Foreign EPR: Assoc. Prof. Dr. Zuraidah Mohd Zain, Dean of Academic Management  University Malaysia perlis  2. Local EPR: Professor Dr. Mohammed Ashraful Alam, Shahjalal University of Science and Technology  *3. Subject Expert: Prof Dr. ABM Shahidul Islam, University of Dhaka* |  |
| 11 | Department of Public Health | September 2017 | September 2017 | October 2017 | Subject expert name by June 30, 2017 |  |
| 12 | Department of Architecture | September 2017 | September 2017 | October 2017 | Subject expert name by June 30, 2017 |  |

At this stage of SA (Self-Assessment), the following selected documents other than the SAM (Self-Assessment Manual) and the CDF (Central Document Folder) are going to be relevant/ helpful. The link for each document is given below. The name of the document is high-lighted below at the end of the link.

1. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**SA-Chart.docx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/SA-Chart.docx)
2. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**SAC-20\_SA-Steps.docx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/SAC-20_SA-Steps.docx)
3. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**document-list.docx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/document-list.docx)
4. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**List-of-Evidences-Needed.docx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/List-of-Evidences-Needed.docx)
5. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**SAC-20\_SAR-Std-1.5.docx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/SAC-20_SAR-Std-1.5.docx)
6. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**2-Dont.docx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/2-Dont.docx)
7. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**Self-Assessment-Exercise-Concept-Procedure.pptx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/Self-Assessment-Exercise-Concept-Procedure.pptx)
8. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**Concepts-of-Guidelines-for-SA-Exercise.pdf**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/Concepts-of-Guidelines-for-SA-Exercise.pdf)
9. [http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**SAC-Meeting.pptx**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/SAC-Meeting.pptx)
10. At External Peer Review (EPR) stage the following document is going to be relevant:

[http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/**Writing-of-SAR-Preparation-for-EPR.pdf**](http://institutions.northsouth.edu/iqac/wp-content/uploads/2016/06/Writing-of-SAR-Preparation-for-EPR.pdf)

The above documents as well as other documents are available on our IQAC resource page <http://institutions.northsouth.edu/iqac/?page_id=116>.